Learning Design T-Shirt Sizing Model

Asana Output, Capacity, Roadblock, and Insight Reporting Template

| Owner / Team | [Name / Team] |
| --- | --- |
| Reporting Period | [Month, Quarter, Sprint, or Date Range] |
| Data Source | Asana export or report with task-level records |
| Audience | Learning leadership, business partners, resource planning |
| Version | [v1.0 / Date] |
| Model principle Score work once at the asset/task level. Initiatives are portfolio containers that roll up the points of their assets. Do not assign separate delivery points to the initiative itself, or work will be double counted. |  |

Use this template to:

Standardize instructional design work tracking across designers and projects.

Separate operational throughput from strategic priority.

Expose blocked work without rewarding blockers as productivity.

Identify output patterns, strengths, resource distribution issues, and Asana adoption impacts.

# 1. Operating Rules

Score completed deliverables and meaningful internal work, not every micro-task or time entry.

Use raw delivery points for throughput. Use strategic priority weighted points for portfolio value conversations.

Track roadblocks separately as explanatory variables; do not add points because a task was blocked.

Use initiative names only to group asset points. Avoid assigning points to both the initiative and the assets inside it.

Discourage inflation: task splitting is acceptable for project management, but only point-bearing records should represent discrete deliverables or approved internal tasks.

Recommended Asana setup Add custom fields for Work Type, T-Shirt Size, Base Points, Complexity Modifier, Strategic Priority Level, Priority Multiplier, Roadblock Days, Roadblock Type, Roadblock Severity, Point Eligible, and Initiative Name. Keep effort/time as a separate field if needed, but do not use it as the primary output measure.

# 2. Core Scoring Formulas

| Metric | Formula | Use |
| --- | --- | --- |
| Raw Delivery Points | Base Points x Complexity Modifier | Measures normalized output. |
| Strategic Weighted Points | Raw Delivery Points x Strategic Priority Multiplier | Supports portfolio priority reporting, not individual productivity ranking. |
| Roadblock Burden | Blocked Days x Roadblock Severity Weight | Explains delivery constraints. |
| Completion Rate | Completed Point-Eligible Tasks / Planned Point-Eligible Tasks | Signals planning reliability and delivery follow-through. |
| Asana Adoption Rate | Tasks with required fields complete / total tasks reviewed | Shows whether reporting quality is credible. |

# 3. T-Shirt Size Reference

| Size | Base Points | General Definition | Examples | Governance Guardrail |
| --- | --- | --- | --- | --- |
| XS | 1 | Very small update or coordination task; limited judgment required. | Minor typo fix, link update, file cleanup, short status update. | Batch repetitive XS tasks where possible. |
| S | 3 | Small asset or contained task with clear requirements. | Job aid update, simple comms asset, SME interview notes. | Must have a clear output. |
| M | 5 | Standard instructional design deliverable or analysis task. | Workshop design, facilitator guide, standard storyboard, basic eLearning update. | Default size for normal ID tasks. |
| L | 8 | Large deliverable with multiple sections, stakeholders, or design decisions. | Full eLearning module, learning architecture, resource hub, complex workshop. | Requires evidence of complexity. |
| XL | 13 | Complex solution with high design depth, multiple dependencies, or high reuse. | Animated eLearning, multi-part curriculum architecture, simulation. | Manager review recommended. |
| XXL | 21 | Exceptional enterprise-level deliverable; use sparingly. | Large integrated learning path component, enterprise simulation, high-risk compliance design. | Requires documented rationale and approval. |

# 4. Point Catalog: External Learning Deliverables

| Deliverable / Asset | Default Size | Effort Score | Point Eligible? | Notes |
| --- | --- | --- | --- | --- |
| Comms asset or launch blurb | XS-S | 1-3 | Yes | Use S only when messaging requires stakeholder review or multiple audiences. |
| Job aid / quick reference | S | 3 | Yes | Use XS for minor update. |
| Knowledge article / resource page | S-M | 3-5 | Yes | Use M when net-new, structured, or multi-section. |
| Facilitator guide | M | 5 | Yes | Use L for complex activities, role plays, or leader notes. |
| Workshop design | M | 5 | Yes | Score each distinct workshop once. |
| Workshop series architecture | L | 8 | Yes | Use only for net-new design of the series structure; do not duplicate each workshop design work. |
| Training deck | M | 5 | Yes | Use S for light updates; L for complex interactive decks. |
| Storyboard | M-L | 5-8 | Yes | Choose L for branching, role-based, or high-stakes content. |
| eLearning module | L | 8 | Yes | Use XL for animation, simulation, or significant interactivity. |
| Animated eLearning | XL | 13 | Yes | Use XXL only when unusually long, complex, or enterprise-critical. |
| Resource hub / learner portal content structure | L | 8 | Yes | Includes architecture, taxonomy, and learner navigation decisions. |
| Learning path architecture | XL | 13 | Yes | Architecture only; individual assets inside the path are scored separately. |
| Assessment / knowledge check design | S-M | 3-5 | Yes | Use M for scenario-based assessment. |
| Pilot / teach-back package | M-L | 5-8 | Yes | Score package, not every calendar invite or reminder. |

# 5. Point Catalog: Internal Tasks, Deliverables and Project Meetings

Internal work rule Internal tasks and meetings should be point eligible only when they produce a reusable output, decision, analysis, plan, or artifact. Routine attendance is tracked for visibility but should not inflate delivery output.

| Internal Work Item | Default Size | Base Points | Point Eligible? | Scoring Guidance |
| --- | --- | --- | --- | --- |
| Project kickoff facilitation | S | 3 | Yes | Eligible when agenda, decisions, scope, and next steps are documented. |
| SME interview / discovery session | S | 3 | Yes | Eligible when notes and implications are captured. |
| Stakeholder review meeting | XS | 1 | Conditional | Eligible only if designer facilitates decisioning and records outcomes. |
| Routine project status meeting | 0 or XS | 0-1 | Usually No | Use 0 unless a material decision, risk, or plan is produced. |
| Project plan / milestone plan | M | 5 | Yes | Eligible when used to coordinate delivery and dependencies. |
| Learning needs analysis | M-L | 5-8 | Yes | Use L when multiple audiences, data sources, or roles are analyzed. |
| Content audit | M | 5 | Yes | Eligible when audit produces recommendations or mapped gaps. |
| QA review / accessibility review | S-M | 3-5 | Yes | Use M when comprehensive and documented. |
| Peer review of learning asset | XS-S | 1-3 | Yes | Use S when feedback is substantive and captured. |
| Backlog grooming / Asana hygiene | XS-S | 1-3 | Conditional | Eligible if it improves reporting quality, removes blockers, or clarifies scope. |
| Template / reusable standard creation | M-L | 5-8 | Yes | Use L when adopted across team or business area. |
| Post-launch evaluation summary | M | 5 | Yes | Eligible when insights and recommendations are documented. |
| Office hours session support | S | 3 | Yes | Eligible when materials, facilitation, and follow-up outputs are included. |
| Ad hoc consult / advisory response | XS-S | 1-3 | Conditional | Eligible when documented advice influences a deliverable or decision. |

# 6. Complexity Modifier

| Level | Multiplier | Use When | Evidence Required |
| --- | --- | --- | --- |
| Standard | 1.00 | Clear scope, known audience, limited stakeholder complexity. | None beyond completed Asana fields. |
| Moderate | 1.25 | Multiple audiences, moderate ambiguity, several review cycles, or moderate technical complexity. | Short rationale in Asana notes. |
| High | 1.50 | High ambiguity, large stakeholder group, high-risk content, complex technology, or enterprise reuse. | Manager/lead validation or explicit rationale. |
| Exceptional | 1.75 | Rare; unusually difficult work with high criticality and cross-functional dependencies. | Approval required; avoid routine use. |

# 7. Strategic Priority Levels

Priority rule Strategic priority creates a separate weighted portfolio view. It should not replace raw delivery points and should not be used alone to compare individual productivity.

| Priority Level | Multiplier | Definition | Use Cases | Guardrail |
| --- | --- | --- | --- | --- |
| P1 - Operational / Local | 1.00 | Important to a team or small audience; limited business risk. | Maintenance, localized enablement, small process change. | Default if no explicit leadership priority. |
| P2 - Business Critical | 1.25 | Supports a committed business outcome, launch, transformation, compliance need, or measurable process adoption. | Role enablement, priority tooling rollout, compliance support. | Requires business owner or program priority. |
| P3 - Enterprise Strategic | 1.50 | Directly supports enterprise-level initiative, executive priority, high-risk transformation, or broad workforce impact. | Large learning path, major system rollout, high-risk regulatory program. | Must be approved and documented; do not apply to every asset within a branded initiative unless each asset is essential to the P3 outcome. |

# 8. Roadblock Variables

| Field | Values | How to Use | Insight It Supports | Do Not Use For |
| --- | --- | --- | --- | --- |
| Roadblock Days | Number | Count workdays where progress was materially blocked. | Blocked capacity, cycle time explanation. | Do not convert directly into productivity credit. |
| Roadblock Severity | 0=None; 1=Minor; 2=Moderate; 3=Major; 4=Stopped | Apply severity weight for burden trends. | Which work streams are structurally constrained. | Do not punish designer for external dependencies. |
| Roadblock Type | SME delay; decision pending; scope change; tech issue; compliance/legal; resource conflict; access issue; other | Capture root cause consistently. | Systemic constraints and escalation needs. | Do not use as free-text only. |
| Controllability | Internal to ID; Partner-owned; Enterprise dependency | Clarifies who can resolve the blocker. | Action planning and escalation. | Blame assignment. |
| Rework Cause | Requirement change; quality issue; stakeholder reversal; inaccurate source content; unclear intake | Use when completed work had to be redone. | Process improvement opportunities. | Inflating points for repeated work without cause. |

# 9. Asana Data Dictionary

| Asana Field | Required? | Allowed Values / Format | Purpose |
| --- | --- | --- | --- |
| Task ID | Yes | Asana task identifier | Deduplication and audit trail. |
| Task Name | Yes | Plain language deliverable or internal task name | Readability. |
| Initiative Name | Yes | Portfolio, program, or project name | Roll up assets without double counting. |
| Work Type | Yes | Deliverable, Internal Task, Meeting, Admin, Maintenance | Segmentation. |
| Asset Type | Conditional | Use point catalog values | Standardized scoring. |
| Point Eligible | Yes | Yes/No | Suppresses micro-tasks and non-output activity. |
| T-Shirt Size | Yes when eligible | XS, S, M, L, XL, XXL | Base estimate. |
| Base Points | Yes when eligible | 1, 3, 5, 8, 13, 21 | Raw scoring input. |
| Complexity Modifier | Yes when eligible | 1.00, 1.25, 1.50, 1.75 | Complexity adjustment. |
| Strategic Priority Level | Yes | P1, P2, P3 | Portfolio weighting. |
| Priority Multiplier | Yes | 1.00, 1.25, 1.50 | Strategic weighted view. |
| Status | Yes | Not started, In progress, Blocked, Complete, Canceled | Pipeline health. |
| Assignee | Yes | Person or team | Distribution and capacity. |
| Start Date / Due Date / Completion Date | Yes | Date fields | Cycle time and timeliness. |
| Roadblock Days | Conditional | Whole or decimal workdays | Constraint burden. |
| Roadblock Type | Conditional | Controlled list | Root cause analysis. |
| Last Updated Date | Yes | Date | Adoption and stale-work signal. |
| Required Fields Complete | Yes | Yes/No | Asana adoption quality. |

# 10. Monthly Insight Summary Template

## Executive Summary

[Summarize total raw points delivered, strategic weighted points, completed assets, key initiatives, and top constraint.]

## Output

[What was completed? Which asset types produced the most points? Which initiatives received the most delivery capacity?]

## Strengths

[Where did the team succeed? Examples: high completion rate, rapid cycle time for a work type, strong P2/P3 delivery, improved Asana hygiene.]

## Resource Distribution

[Where are points, roadblocks, or overdue tasks concentrated by person, initiative, business partner, work type, or priority level?]

## Risks / Constraints

[What blocker types created the highest burden? Which initiatives have high planned points but low completion?]

## Asana Tool Adoption Impact

[How complete and reliable is the data? Are missing fields, stale tasks, or inconsistent scoring affecting the story?]

## Recommended Actions

[What should leadership do next? Examples: escalate SME delays, rebalance workload, clarify intake, enforce required fields, adjust priority labels.]

# 11. Analysis Prompts to Use With Asana Data

How to use these prompts Paste the structured Asana export summary or table after each prompt. Replace bracketed text with your reporting period, team, or business area.

## Output and portfolio summary

Using the Asana task-level data below, summarize completed raw delivery points, strategic weighted points, completed asset count, and top initiatives by completed points for [reporting period]. Separate raw throughput from strategic weighted view. Flag any possible double counting or non-point-eligible work that appears in the totals.

## Strengths and repeatable wins

Analyze the data for team strengths. Identify where the team delivered efficiently by asset type, initiative, assignee, priority level, and cycle time. Include evidence from completed points, completion rate, blocker burden, and field completeness.

## Poorly distributed resources

Look for workload imbalance across assignees and initiatives. Compare planned points, completed points, open points, blocked days, overdue tasks, and P2/P3 concentration. Identify whether the imbalance appears driven by workload assignment, blocker concentration, priority concentration, or Asana data quality.

## Roadblock root cause analysis

Analyze roadblock burden by blocker type, severity, controllability, initiative, and business partner. Distinguish between ID-owned blockers and partner- or enterprise-owned blockers. Recommend the top 3 escalation or process actions.

## Asana adoption impact

Evaluate the reliability of the reporting data. Calculate or estimate required-field completeness, missing points, missing priority, stale tasks, tasks without completion dates, and point-eligible tasks without size. Explain how adoption gaps may distort output, resourcing, or performance conclusions.

## Leadership narrative

Convert the analysis into a concise executive narrative: what was delivered, what mattered most strategically, what constrained delivery, where resources may be misaligned, and what decisions leadership should make next. Avoid ranking people without context from blockers and data completeness.

## Governance check

Audit the scoring for inflation risks. Flag tasks that may be split too granularly, meetings that may not have outputs, repeated strategic priority labels, excessive complexity modifiers, or initiative-level records that duplicate asset-level points.

# 12. Scoring Governance Checklist

Are initiatives used only as containers, not as separate scored deliverables?

Are point-bearing meetings tied to decisions, outputs, or documented next steps?

Are priority multipliers applied consistently and approved for P3 work?

Are complexity modifiers supported by rationale when above 1.00?

Are blocked days tracked separately from delivery points?

Are repeated small tasks batched or marked non-point-eligible when appropriate?

Are required fields complete enough to support leadership reporting?

Are raw throughput and strategic weighted points shown side by side?

# 13. Worked Example

| Initiative | Deliverable | Base | Complexity | Raw Points | Priority | Strategic Weighted |
| --- | --- | --- | --- | --- | --- | --- |
| Project 1 | ILT Workshop (4) | 5 each | 1.00 | 20.0 | P2 x 1.25 | 25 |
| Project 1 | Resource hub | 8 | 1,00 | 8.0 | P2 x 1.25 | 10 |
| Project 2 | Animated (4) eLearning | 13 each | 1.50 | 78 | P3 x 1.50 | 117 |
| Project 2 | Resource hub | 8 | 1.00 | 8.0 | P3 x 1.50 | 12.0 |
| Interpretation The example is a simplified view that is focused only on final deliverables and not the complex full project scoring. This draws out the resourcing need difference between a mid-sized ILT series Note: The initiative does not get separate points; it simply rolls up the assets inside it. |  |  |  |  |  |  |